## Timetable
Wirral Metropolitan Borough Council - Regulatory & Enviromental Services Replacement Software - CRM 103501
|  | Day | Date | Time | Notes
Pre-Tender Activities
Contract notice published: | EXT
Expression of interest sent: | INT
PME sign-on approvals given: | INT |  |  |  | Opportunuity was signed-on based on an NPS request for an extension from the client
Project Board Review | INT |  |  |  | Previously GT&I
Tender Start Activities
Documentation Received: | EXT |  |  |  | Date received by Bid Management Team
Bid support engagement | INT |  |  |  | TBC
Bid Kick-Off: | INT | Wed |  |  | Scheduled 25/09/19
Clarification Deadline: | EXT | Mon |  |  | http://www.the-chest.org.uk
Solution / Service and Proposition Design
Solution / Services Design Workshop | INT
Win Theme Development Workshop | INT
Financial / Legal / Commercial
Pricing Preparation: | INT | Thur |  |  | Adrian Bancroft to confirm
CREM & sign-off approvals | INT | Fri |  |  | Adrian Bancroft to confirm
Pre-PAB: | INT |  |  |  | Russell Holmes to confirm
PAB: | INT |  |  |  | Russell Holmes to confirm
Authoring and Written Review
Written Submissions: | INT
Bid Management Review: | INT
Blue Team Review: | INT | Mon
Red Team Review: | INT | Wed
Final amendments and changes: | INT | Thur |  | 17.00 | Deadline by which the bid will be handed to Bid Support, after which no further amends will be possible.
Production Activities | INT
Initial formatting of responses: | INT
Final format for Red Team: | INT
Date and time of INTERNAL deadline (UK time) | INT |  |  |  | Formatted and ready for submission
Date and time of INTERNAL deadline (local time if diferent) | INT
Client submission deadline (UK time): | EXT | Mon |  | Noon
Client submission deadline (local time - if different): | EXT
Delivery method / format of response (email, electronic upload or postal) | EXT
Delivery address (email, URL or postal address) | EXT |  |  |  | http://www.the-chest.org.uk
Delivery limitations (max upload size, office opening hours) | EXT
Post Tender
Post Bid Review | INT |  |  |  | For all Prjoject Board Review (previously GT&I) opportunities and any bids where the Bid Manager believes the bid process failed and improvements need to be made
Bid Closedown: | INT |  |  |  | Identify good quality re-usable content for inclusion within Knowledge Base
Clarification Questions: | EXT |  |  |  | Another tab can be created if questions need allocation to the bid team for response
Reference Visits: | EXT
Presentations/Interviews: | EXT
Notification of Preferred Supplier: | EXT
Notification of Intention to Award Contract: | EXT
Confirm Contract Award: | EXT
Contract Start: | EXT
Checklist
Governance/Approvals (Bid Planning Stage)
Legal Engagement | INT |  | Insert Date |  | Should be within 24 hours of allocation of bid
Directors Signature Request Required? | INT |  | No selection made |  | Hard/soft copy signature required. Number of signatures required and whether witness signature required (Legal input needed)
Director's Authorisation to Submit Required? | INT |  | No selection made |  | No signature required - approval to submit (i.e. name required on forms etc.)
Governance Model Confirmed? | INT |  | No selection made |  | Does it require PAB approval? Is it an international bid - if so who needs to be involved in the bid process?
PME Sign-on approval received from other business areas, e.g. Solutions/Services/Health etc. (if required) - Hosting, Cloud, Develpment? | INT |  | No selection made |  | Insert date approved and add notes as to which business area approved
Framework-related (Bid Planning Stage)
Is the opportunity for a new Framework Agreement? | INT |  | No selection made |  | Refer to Legal and advise Frameworks Service Desk & Carol Webb
Is the opportunity a call-off contract under a Framework Agreement? | INT |  | No selection made |  | Ensure Frameworks Service Desk is aware and highlight to Legal. For example, Scottish Government, Welsh Government, Crown Commercial Service (CCS), NHS Shared Business Services (NHS SBS) etc.
Third Parties FRAMEWORKS (Bid Planning Stage)
Are we using a sub-contractor - if so are they on the approved list of sub-contractors? | INT |  | No selection made |  | Confirm with Legal and, where a Framework Call-Off, the Frameworks Service Desk that any sub-contractors we are using are on the appropriate approved list of sub-contractors.
Confirmation that sub-contractor has appropriate security and vetting procedures in place | INT |  | No selection made |  | Ensure standard statement is sent to sub-contractor and confirmation is received back prior to releasing tender documentation.
Third Parties OTHER BIDS (Bid Planning Stage)
Confirmation that sub-contractor has appropriate security and vetting procedures in place | INT |  | No selection made |  | Ensure standard statement is sent to sub-contractor and confirmation is received back prior to releasing tender documentation.
Confirmation teaming agreement is in place/in progress with relevant sub-contractor for delivery of the contract. | INT |  | No selection made
Are there any new commitments we are making that mean we need to update our processes? | INT |  | No selection made |  | Make legal aware of any commitments made by delivery and also of any new delivery requirements Make legal and Ian Gregory aware of any commitments in the bid relating to sub-contractors - for example, Health and Safety, Environmental, Equality etc. For example, do we vet our sub-conractors? Add to list of subcontractor questions/issues on bid portal
Miscellaneous (Bid Planning Stage)
Bid Manager has logged onto the client portal and checked all requirements and documentation has been dowloaded and captured | INT |  | No selection made |  | Assigned Bid Manager to log onto client portal as soon as possible after allocation - this should typically be prior to the bid kick off.
Insurance Certificate Required? | INT |  | No selection made |  | Request from James Iveson / Mark Morrell and save to Knowledge Base
Miscellaneous
Insurance Certificate Requested | INT |  | Insert Date |  | Allow a minimum of one week before despatch. Request from James Iveson and Mark Morrell, save copy to Knowledge Base
Escalation required? | INT |  | No selection made |  | Triggers - resourcing issues, solution not agreed; agreed deadlines missed
Were there issues during the bid process? | INT |  | No selection made |  | Report to Carol any issues that arise during bid process, i.e. - no or inadequate Blue/Red team review Follow the bid closedown activities guide
Changes to bid Plan & Tracker - new steps which we need to follow:
1. Complete 'bid support requirements', noting new requirements. Detailed info re formatting, production and clarifications, highlighted in grey will automatically update in the 'bid support requirements' tab when completing the 'timetable' tab. Check all required cells are complete.
2. Notify bid support, via email, the bid plan is available for their review / consideration.
3. Schedule a 15 minute call to discuss and agree the timetable and requirements in line with the bid plan with bid support. This formalises bid support engagement.
4. Following kick-off, where relevant & where possible identify the re-use of any existing material & notify bid support.

## Bid Support Requirements
Wirral Metropolitan Borough Council - Regulatory & Enviromental Services Replacement Software - CRM 103501
Our Section | Title | Client section / ref (Reference the client document and page numbers for copy / paste purposes) | Notes / comments
1 | Method Statement
2 | Social Value
3 | Pricing
4 | Declarations
Appendices
1 | Project Plan
2 | APIs
3 | Draft Licence Agreement
4 | Support & Maintenance Agreement
5 | Certification of PCI DSS Compliance
| Template and Formatting Instructions | Detailed information |  | Notes
| Client or NPS Template | Client only |  | No need to format the templates
| Font size and font type | As above
| Any client specific file names or titles required | No
| Any header / footer requirements | NPS standard for Section 4
| Paper size (particularly relevant for international tenders) | No
| Re-use of material where identified | Yes
| Submission / Production Instructions | Detailed information & dates | Time | Notes
| NPS or ANO prime | NPS | n/a
| Date and time of INTERNAL deadline (UK time) | 0 | 0:00
| Date and time of INTERNAL deadline (local time if diferent) | 0 | 0:00
| Date and time of client submission (UK time) | 0 | Noon
| Date and time of client submission (local time if different) | 0 | 0:00
| Delivery method / format of response (email, electronic upload or postal) | 0 | n/a
| Delivery address (email, URL or postal address) | http://www.the-chest.org.uk | n/a
| Delivery limitations (max upload size, office opening hours) | 0 | n/a
| Confirmation of labels supplied | Y / N | n/a
| Clarification Instructions | Detailed information | Time | Notes
| Clarification deadliine | 0 | 0:00
| Delivery method / format of response (email, electronic upload or postal) | http://www.the-chest.org.uk | n/a
| Delivery address (email, URL or postal address) | http://www.the-chest.org.uk | n/a
Note on B19: Sue Bellairs: Where any anomalies exist, add specific requirements in the ‘notes & comments’ column of the relevant sub-section (e.g. where no changes to the submission form are permitted - use client template or the template differs to the overall formatting instruction, font type etc.
Note on C27: Sue Bellairs: Detailed info, date & times are automatically updated when completing the timetable tab

## Detailed Allocation & Tracker
Wirral Metropolitan Borough Council - Regulatory & Enviromental Services Replacement Software - CRM 103501
Section | Question | Topic/Requirement | Maximum words | Score / Weighting | Question Owner | Supporting Resources | Notes / Guidance / Instructions | OVERALL STATUS | Bid Manager | Review 1 (Blue) | Review 2 (Blue) | Review 3 (Blue) | Review 4 (Blue) | Review 5 (Blue) | Review 1 (Red) | Review 2 (Red) | Review 3 (Red) | Review 4 (Red) | Review 5 (Red)
LOT 1
|  | Tenderers are required to complete the compliance table below. This table will form a critical part of the appraisal process. (These will replicate method statements for compliance purposes). |  |  | jason/jon
| 1 | The system shall be capable of receiving and submitting data and documents via multiple sources (Including but not restricted to Web Portals, Gov.uk, Planning Portal - including the new Building Control update, Submit-a-Plan, National Land Information Service, Symology.) either in real time or by batch processing. The above shall allow applicants to resubmit application with modifications including updated plans, please detail how you will enable this.
| 2 | Online payments as part of online submission of application and online payments after submission of application to automatically update the back-office system with the receipt of payment.
| 3 | The system shall accept unique references from third party applications, when cases are created externally from the sources mentioned in 2.2.4.1 above.
| 4 | The system to allow Users to have multiple case files open at any one time to allow updating and responding to enquiries.
| 5 | The system to have Address validation via UPRN with online mapping and integration to council LLPG to prevent incorrect scheme applications
| 6 | Users should be able to look up a property and see all customer profiles and associated case records linked to that property and drill down into its complete history for all disciplines within the system for which they have security privileges.
| 7 | All information relating to the property shall be entered in one central place negating the need to re-enter information into several areas of the system
| 8 | The system shall be able to automatically update the status of a case, record or customer profile based on the fulfilment of predefined criteria. System admin users shall be able customise these criteria to allow for status updates to be customised. The system shall be prepopulated with a list of standard statuses.
| 9 | The system shall be capable of performing and recording all interactions between the Council and its stakeholders, including but not limited to: - Service requests - Bookings and payments - Inspections, visits and action - Formal enforcement action and legal proceedings - Consultations - Permits and licenses
| 10 | The system shall allow users to drag and drop multiple documents at once and attach them to a property/case/customer profile. The system shall allow system users to delete and amend attached documents dependent on their security privileges. All documents attached to records, cases or customer profiles shall be instantly available to all users with appropriate security privileges.
| 11 | The system shall have a record locking or alert mechanism to prevent multiple users editing the same record concurrently. The system shall alert the user the record is currently in use and identify the user.
| 12 | The system shall create and auto-generate unique case identifiers, the format of which shall be customisable by the Council system administrator
| 13 | Users shall have the ability to reject applications made online and send the applicants a message detailing why it has been declined. Once rejected, the application will be removed from any list of active applications and from any workflows.
| 14 | The system shall allow for all aspects of records or cases to be alterable after creation, dependant on user's security privileges.
| 15 | All fields to be auditable, as there is a need to know person responsible for input/amendment/deletion. | [17 empty] | Not Ready
| 16 | The system shall enable the classification/flagging of types of customers/properties | [17 empty] | Ready for Review
| 17 | The system shall be capable of creating a sufficient number of customisable roles and competency skillsets that can be applied to users and customers. Users shall be able to assign multiple roles to a single users/customer. These roles and skillsets shall dictate what areas of the system the user or customer can access and what records and fields can be viewed and or edited. The role assigned to a user shall also dictate which templates/reports they will have the ability to see and run. It is intended that roles and skillsets shall allow workflows to automatically assign tasks to users with predefined skillsets/roles and to automatically shift tasks between users once the case has reached a predefined status necessitating a change in users’ skillset/role. By linking roles and skillsets to staff competency it is envisaged that the system shall allow areas of weakness within the staff competency matrix to be readily identified. | [17 empty] | Minor Comments
| 18 | The system shall support time recording. There shall be the ability to assign different salary costs for different officers or roles to allow the cost of an intervention to be calculated or an officer's productivity. | [17 empty] | Approved
| 19 | The system shall automatically insert data into dependant fields subject to rules. There shall be a facility to override this where necessary. | [17 empty] | Not Applicable
| 20 | Provide all required fields for each service area to process a record from start to finish to meet legislative requirements.
| 21 | The system may allow for validation rules to be set on any field within the system including online submission e.g. mandatory fields. The system may have settings to require data to be entered in the correct format before being pulled into the back-office system, using list options where available, e.g. titles, addresses, dates, currency etc. The character type and limits for every field will be customisable.
| 22 | Ability to record and change the name and status of attached documents. e.g. Plans submitted can be designated, superseded, approved or refused which would also be displayed online, once reviewed by an Officer.
| 23 | Ability to mark documents in DMS as public, private and consultee etc
| 24 | The system may be fully configurable allowing for the creation of additional fields with customisable characters limits, content controls and field naming conventions.
| 25 | The system may facilitate Live Chat between active users, including the supplier
| 26 | When creating actions within the diary or calendar, the system may allow users to link to documents stored against the case record within the diary entry allowing the document to be opened remotely without searching for the primary record.
| 27 | The system to provide an UNDO function that allows users to reverse any action that happens behind the scenes in a record as a result of data being entered.
| 28 | The system may keep track of recently opened and most often requested records so that users/customers can open them from a list without searching.
| 29 | The system may provide error messages that describe the full nature of the error, including the field or function that has caused it and allow the user to navigate to this field to fix the issue.
| 30 | All properties shall be stored using the UPRN as the primary reference.
| 31 | The applications shall link to the councils BS7666 addressing infrastructure and all addresses shall be derived from this infrastructure and shall update automatically when the corporate address is updated.
| 32 | Daily/weekly/monthly COU import of LLPG as well as capability of direct updates from Corporate Address Gazetteer software.
| 33 | To have batch printing function
| 34 | Spatially enabled integrated solution (generate case record from plotting boundary of the application on GIS to populate fields in the database from MapInfo tab files)
| 35 | Perform spatial search to display specific fields from the case file in GIS e.g. case number, proposal, location, decision, date of decision
| 36 | MapInfo compatible GIS (MapInfo tab files for all Wirral Council spatial data)
| 37 | The application shall draw data from the corporate GIS solution and/or other corporate applications to allow: - addresses be extracted from a GIS by either drawing boundaries or selecting individual properties - Selection of neighbours based on spatial data from corporate addressing data - Auto-generate consultees from spatial layer - Analysis of spatial data from the corporate GIS - Analysis and linking of property or person-based records The system shall record details of all representations sent and received responses which shall be automatically assigned to the appropriate record in the system. The data received shall be editable and redactable (where allowed by the file type).
| 38 | The GIS Interface shall provide tools to - Geo-reference images - On the fly spatial analysis - Plot point, line and polygon features - Copy, edit polygon - Capture multiple location polygons for a single case record - Measure existing features automatically - Map printing - Zoom to & pan to selected features - Search for an address from the corporate address database - Measure new features via button clicks - Add new layers - Creation of buffer zones. - Capability to view additional MapInfo tab files by adding via layer control The tool shall also allow for the measuring of areas and calculating angles.
| 39 | Print current map window to a selected scale e.g. A4, portrait/landscape with logos, textual information, copyright acknowledgement, watermarking to PSMA requirements, save as PDF. Add information to the print template using free text fields.
| 40 | GIS search by case number, partial address, or postcode to find site on map
| 41 | The system may have the ability to create exportable lists from GIS following the selection of a buffer zone; this may allow users to pre-select what kind of record(s) they are interested in, highlight an area and export a list of relevant records from within the area.
| 42 | Customisable embedded workflow processes for all service functions and processes
| 43 | View a configurable dashboard of all cases on system start up including, for instance;  List of new planning applications  List of new pre-applications  List of open cases with additional actions / updates planning applications  List of open cases with additional actions / updates pre-applications  List of cases approaching KPI breaches  List of cases breached  Case status  Cases closed in last X days  List of cases by Case Officer
| 44 | Facility to export raw data in industry standard forms to allow data analysis by partners etc. e.g. Excel
| 45 | Ability to create 'on-the-fly' PDF document for system documents to be emailed e.g. saving maps from GIS to DMS
| 46 | The system shall be capable of automatically producing and sending consultations via email or letter when predefined criteria are met (as controlled by system admin users).
| 47 | The system shall allow for the scheduling of reports and templates to auto generate. Capability to default correspondence from case record to be sent by email where an email address is provided
| 48 | All data retrieved from searches, reports, templates and selected mapping layers shall be exportable to standard file formats. All dates stored and exported by the system shall be in the standard UK date format.
| 49 | The system shall have the ability to redact any information from documents submitted/uploaded. This shall either be provided within the system itself or be compatible with third party software to redact documents.
| 50 | Skillsets shall be used by the system in order to assign tasks and workflows to a user.
| 51 | Document production audit in order to identify who has issued the document.
| 52 | Document restriction by job role security permission e.g. only Principal Officers to issue decision notices.
| 53 | A field is required to record sign off. Only the name of the person logged in can be entered, and once entered cannot be amended. Principal officers to have the ability in the system to authorise Officer Reports prior to being published online. Principal officers sign off other matters too!
| 54 | The system may enable the location, date, time stamp and other meta data attached to documents/images uploaded to or downloaded from the system to be retained. This may include any GPS/Geo location services.
| 55 | The system shall be capable of creating and displaying any statutory public register online using any data contained within the system including spatially captured data.
| 56 | Customers can search the online registers for their application/complaint using the following criteria: Application Reference Planning Portal Reference Description Keyword Application Type Ward Conservation Area Agent Status Decision Appeal Status Appeal Decision Development Type Address Date Received Date Validated Date Committee Decision Date Appeal Decision Date Not case sensitive Any date field search to allow date range search Separate Weekly/Monthly list of applications to be able to search all or by Ward for date range of applications validated or applications decided that week or month.
| 57 | To have the capability to digitally stamp plans as approved or refused on the appropriate drawing plus a field within DMS for each document to be marked/updated to show which drawings/plans have been approved or refused. This field to also be displayed online so the public can quickly identify the plans which have been approved or refused and save them and the case officer wasted time opening all the other plans to identify those which have been approved/refused.
| 58 | To have the ability to mark a current record as special circumstances to automatically extend the retention period (for business reasons) from the standard/scheduled retention period for complex, or large, or of public interest case records.
Planning
| 59 | Development Management service must go-live with full functionality required to deliver the service from start to finish on the same day (cannot be a phased approach) e.g. database, GIS functionality, online register and Document Management functionality all live on the same day.
| 60 | Full back office integration with One App Form submission from Planning Portal.
| 61 | Amended online submissions to only update the changed information or documents (not duplicate the whole file and all of the documents).
| 62 | Generate case record from GIS. Search GIS by any of the following: Street Name, Post Code/partial post code, partial location address.
| 63 | Capture polygon of application boundary to generate new case record, update case record with all associated data from spatial area e.g. policy and constraints, ward, previous planning applications, previous building control applications etc. to relevant fields. Auto selection of consultees from spatial area to update case record.
| 64 | Allow input of out of area address for contacts.
| 65 | Union geometry to allow capture of more than one spatial polygon for a single case record.
| 66 | Send email alert messages or notifications to internal and external addresses relating to status of application, tracked changes, task reminder etc. set up and selection to be configurable by the user.
| 67 | Field validation - client system admin to be able to set field validation rules e.g. mandatory input, default value, cross-field validation, calculate and update other fields from value entered in field, pop up screen messages relevant to value entered etc.
| 68 | Documents to be configurable so one letter can be generated to cover many scenarios e.g. a single document can be used for Approval and Refusal Decision Notice but use code to output relevant text for Decision type, Act, Appeals Decision Summary etc. dependent upon Field values on the case record.
| 69 | Capability to default documents to be sent by email rather than print where an email address is held.
| 70 | Standard text to choose from for Invalid reasons as well as unique, editable text.
| 71 | Select neighbour addresses from GIS either by polygon, circle or point selection to auto populate the case record to generate neighbour letters.
| 72 | Public to be able to submit comments online to automatically update the case record. Commenter to received auto email confirmation of receipt of comment when authority accept the comment into the back office case record.
| 73 | Create receipts on case record showing relevant payment details, to produce receipt, remittance and to be able to process funds. Create receipts for requests for copies of decision notices etc. but not held against a case record.
| 74 | Consultee Access to enable consultees to login in to view details and documents online and to be able to submit comments online. Comments submitted and accepted online to update the case record.
| 75 | Comments from public or consultees received online automatically update case record with reply/comment received date, whether objects, supports or neutral, name, address and email of commenter. Ability to filter addresses of those sent to update with reply details or if no match to create new (for unsolicited comment received). Show online the count of objections, support and neutral comments received and option to show address of commenter and/or comment text online. Send notification to case officer via workflow manager that a new comment received. Same as above for consultees.
| 76 | Ability to re-consult neighbours using original addresses and enabling days to reply to be amended by user to less than standard consultee period.
| 77 | Ability to create document to output all comments received, date comment received and name and address of commenter or consultee.
| 78 | Creation of all standard reports including PS1/2, Press Notice
| 79 | Officers report/committee report capability to share report for input, track changes, accept or reject changes, version control
| 80 | Officer's report and Decision Notices preferably configured to use MS Word.
| 81 | Separate fields to record comments from consultees, neighbours, ward councillors/MPs so that they can be pulled through to the officer report.
| 82 | Auto-populate from GIS the planning history (previous planning applications) to relevant field so that can be brought through to officer report. Display planning history in chronological order.
| 83 | Conditions and Reasons standard codes and text which can be edited and unique codes for free text. Ability to copy conditions and reasons from another case record.
| 84 | Insert site map from GIS to officer report showing site edged red and annotations where required and displaying Ordnance Survey copyright acknowledgement. Ability to print maps to scale, scale of choice.
| 85 | Safeguards for Decision Notice to prevent being sent before end of Statutory Consultation Date, being sent before Legal Agreement signed for S106, being sent if not signed off by Principal Officer, being sent if already been dispatched. Safeguards to prevent Decision Notice being created if not got any conditions and reasons.
| 86 | Ability to print or send Decision Notice by email.
| 87 | Publish decision notice or Officer Report online but only if logged as authorised to do so by the Principal Officer.
| 88 | Appeal statement integrated with MS Word to be able to save as pdf to upload to the Planning Inspectorate from case record.
| 89 | Ability to update compliance status for each condition for Discharge of conditions.
| 90 | Section 106 Legal Agreements to have minimum of the following fields on the case record: signed date, details (memo field), Compliance notes (memo field), Funds received and dates.
| 91 | Multi tag documents to upload to DMS as one but index individually. Bulk upload (drag and drop to DMS)
| 92 | Clear preview of documents before upload to enable to save as correct document type to DMS.
| 93 | Digitally stamp plans as approved or refused on the appropriate drawing. Field within DMS case record to show which drawings have been approved or refused to also be displayed online.
| 94 | Capability to scan all documents for a case file in one go regardless of paper size for each varying between A4 to A0, then index to save as individual document types with associated metadata such as sensitivity, document description etc.
| 95 | Workflow manager to show brief details of case including expiry date. Ability to sort workflow to suit role e.g. planning officers to see own case load and to be able to filter and sort dependent on requirements. Principal Officers with line management role need to be able to see workload for all officers or group of officers and to be able to filter and sort dependent on task e.g. allocate case record or sign off officer report. Need to be able to select a case from workflow to open case record. Workflow messages / notifications for each stage of process to be configurable by system admin.
| 96 | Fields to be locked once application has been determined so that cannot be amended other than by supervisor (system admin) security level. Fields to be locked determined and configured by system admin.
| 97 | Auto detection and redaction of personal and sensitive information.
| 98 | Online payments as part of online submission of application and online payments after submission of application to automatically update the back-office system with receipt of payment.
| 99 | The system to be capable of generating a request for a refund and communicating the requirements to the Councils chosen financial system.
| 100 | The system to have the capability to generate Council Committee reports including capability to insert map produced from integrated GIS showing site edged red into any report or document.
| 101 | The system to be capable of providing functionality for Pre-Planning advice service for minor, medium and major developments.
| 102 | Mobile solution to enable the same functionality as specified above must be met for Planning.
Enforcement
| 103 | Development Management Enforcement service must go-live with full functionality required to deliver the service from start to finish on the same day (cannot be a phased approach) e.g. database, GIS functionality, online register and Document Management functionality all live on the same day.
| 104 | Generate case record from GIS. Search GIS by any of the following: Street Name, Post Code/partial post code, partial location address.
| 105 | Capture polygon of application boundary to generate new case record, update case record with all associated data from spatial area e.g. policy and constraints, ward, previous planning applications, previous building control applications etc. to relevant fields.
| 106 | Allow input of out of area address for contacts.
| 107 | Union geometry to allow capture of more than one spatial polygon for a single case record.
| 108 | Insert site map from GIS to officer report or document e.g. Enforcement Notice showing site edged red and annotations where required and displaying Ordnance Survey copyright acknowledgement. Ability to print maps to scale, varying scales.
| 109 | Send email alert messages or notifications to internal and external addresses relating to for e.g.: status of application, tracked changes, task reminder etc. set up and selection to be configurable by the user.
| 110 | Field validation - client system admin to be able to set field validation rules e.g. mandatory input, default value, cross-field validation, calculate and update other fields from value entered in field, pop up screen messages relevant to value entered etc.
| 111 | Documents to be configurable so one letter cover many scenarios.
| 112 | Capability to default documents to be sent by email rather than print where an email address is held.
| 113 | Create receipts on case record showing relevant payment details for Formal Complaints, High Hedges, and Enforcement Appeals etc. to produce receipt, remittance and to be able to process funds. Create receipts for requests for copies of Enforcement Notices etc. but not held against a case record.
| 114 | All actions to be recorded as part of an electronic log for each case file e.g. telephone calls, letters sent, notices served etc
| 115 | Multi tag documents to upload to DMS as one but index individually. Bulk uploads (drag and drop to DMS).
| 116 | Capability to scan all documents for a case file in one go regardless of paper size for each varying between A4 to A0, then index to save as individual document types with associated metadata such as sensitivity, document description etc.
| 117 | Workflow manager to show brief details of case including expiry date. Ability to sort workflow to suit role e.g. Enforcement officers to see own case load and to be able to filter and sort dependent on requirements. Principal Officers with line management role need to be able to see workload for all officers or group of officers and to be able to filter and sort dependent on task e.g. allocate case record or sign off officer report. Need to be able to select a case from workflow to open case record. Workflow messages / notifications for each stage of process to be configurable by client system admin.
| 118 | High Hedge online calculator.
| 119 | Mobile solution to enable the same functionality as specified above must be met for Enforcement.
Tree Preservation Orders
| 120 | Provide all fields required to process a Tree Preservation Order from start to finish to meet legislative requirements
| 121 | Spatially enabled integrated solution (generate case record from plotting boundary of the application on GIS to populate specified fields in the database from MapInfo tab files)
| 122 | Generate auto consultees from spatial layers when creating a new record.
| 123 | Spatially select interested parties addresses for sending list of addresses in word document for mail merge by Legal using addresses from the LLPG (using polygon or point selection
| 124 | Using GIS to create and link each (polygon) category (area, group, woodland, individual) of TPO to a single case record. Capability to link multiple polygons to a single case record. Allow numerous for each category.
| 125 | Annotate map (e.g. edge site boundary in red, type text or mark area), save map as pdf to DMS. Print map to scale. Print to various sizes. Edit and add legend, add watermark, Ordnance Survey Copyright Acknowledgement.
| 126 | Agile solution for site visits to enable plotting of polygon for TPO categories (area, group, woodland, individual) to specific style as required by legislation, input textual details to case record to produce documents to be sent by email. Retrieve and save documents to DMS, upload photos to DMS
| 127 | Generate workflow task for TPO key stages
| 128 | Generate email alerts or notifications as reminders to do tasks
| 129 | Generate committee reports. Capability to insert map produced in GIS showing site edged red or showing polygons for TPO into any report or document. User specification of search criteria to easily provide reports to answer Freedom of Information requests
| 130 | Online TPO Register with associated documents from DMS for public viewing
| 131 | Mobile solution to enable the same functionality as specified above must be met for TPO
Tree Works Applications
| 132 | Provide all fields required to process a Tree Works Application from start to finish to meet legislative requirements
| 133 | Full back office integration from Planning Portal One App Form submission
| 134 | GIS search by address, capture polygon, create case record from polygon, update location site address, conservation area and previous Tree Works Application reference number from tab file to relevant field in case record. Auto select consultees from captured polygon to case record.
| 135 | Online register of Tree Works Applications - client system admin able to create/amend selection criteria for those which should show online. Associated documents from DMS to be displayed via the case record register.
| 136 | Consultee Access to enable consultees to view details and documents online and to be able to submit comments online. Comments submitted and accepted online to update the case record.
| 137 | Neighbours/public to be able to view details and documents online and to submit comments online. Comments submitted and accepted online to update the case record.
| 138 | Generate officer reports. Capability to insert map produced in GIS showing site edged red or showing polygons for Tree Works Applications into any report or document. User specification of search criteria to easily provide reports to answer Freedom of Information requests
| 139 | Mobile solution to enable the same functionality as specified above must be met for Tree Works Applications
Building Control/Land Charges/Street Naming and Numbering
| 140 | To have the ability to support the full case lifecycle for Building Regulations and related applications including dangerous structures, demolitions, scaffolding and hoardings to include recording, generation of customisable documentation, status monitoring and decision making, with the facility to automatically inform applicants of the progress being made with their applications
| 141 | Have the ability to support the full case lifecycle for Local Land Charge searches functions including the management of the LLC1 register and CON29O/R. to include recording, generation of customisable documentation, status monitoring and decision making, with the facility to automatically inform applicants of the progress being made with their applications
| 142 | To have the ability to support the full case lifecycle for Street Naming and Numbering and related applications to include recording, generation of customisable documentation, status monitoring and decision making, with the facility to automatically inform applicants of the progress being made with their applications
| 143 | The software must have single sign on with an integrated system across functions that reuses information across all areas to enable more efficient working with any existing customer information already held in the system, to reduce customer re-keying their details i.e. name, address etc. The result shall allow users to look up a property and see all customer profiles and associated case records linked to the premises; they shall then be able to drill down into its complete history for all disciplines within the system for which the Council has purchased a licence.
| 144 | The supplier must clearly identify which aspects of the system can be fully customised by Council System admin users and which cannot be modified to avoid any contractual conflicts.
| 145 | The software must be available 24/7/365 from any location
| 146 | The system shall be capable of performing and recording all interactions between the Council and its stakeholders, including but not limited to: - - Service requests - Bookings and payments - Inspections, visits and action - Formal enforcement action and legal proceedings - Consultations
| 147 | The system shall have a record locking or alert mechanism to prevent multiple users editing the same record concurrently. The system shall alert the user the record is currently in use and identify the user.
| 148 | The system may allow for validation rules to be set on any field within the system including online submission e.g. mandatory fields. The system may have settings to require data to be entered in the correct format before being pulled into the back-office system, using list options where available, e.g. titles, addresses, dates, currency etc. The character type and limits for every field will be customisable.
| 149 | The system shall have numerous, amendable, fee calculators to suit the service areas. These calculators shall allow for the customisation of locally set fees with multiple permutations. The system shall be capable of storing multiple extra fees on a case by case basis. The system shall be capable of storing separate fees within a case and auto populating the required fee based on customisable rules (e.g. if a building control case covers 120 plots, the fees due for each plot shall be automatically added to the fee calculator). The system may allow fees to be paid in stages or deferred and added to other fees and be able to apply discounts.
| 150 | The system shall be seamlessly integrated with a calendar/diary facility either native to the system or provided by Microsoft Outlook allowing users to create bookings within the system. This shall also allow for multiple users’ calendars to be updated concurrently. This must be a 2- way communication with online booking of appointments and scheduling of visits/inspections, e.g. determining a user’s availability to facilitate the booking of time slots. There shall be no restrictions on the number of calendars that can be linked to the appointment/booking function.
| 151 | The system shall be capable of automatically producing and sending consultations via email or letter when predefined criteria are met (as controlled by system admin users). Ability for consultees and interested parties to comment on cases with responses received automatically uploaded into back office system.
| 152 | All user accounts and security settings should all be capable of maintenance by system administrator. Management of user accounts and permissions should be available including restricting permissions to individual; forms, fields, reports, and documents.
| 153 | Users shall have the ability to create child records under certain parent record types, e.g. adding plots to a building control application.
| 154 | The system shall be able to automatically update the status of a case, record or customer profile based on the fulfilment of predefined criteria. System admin users shall be able customise these criteria to allow for status updates to be customised. The system shall be prepopulated with a list of standard statuses.
| 155 | The system shall create and auto-generate unique case identifiers to categorise the type of service and work type, the format of which shall be customisable by the Council System Administrator. This will enable statistics to differentiate between different types of building work, levels of complexity etc.
| 156 | The system shall be capable of creating sufficient numbers of customisable roles and competency skillsets that can be applied to users and customers. Users shall be able to assign multiple roles to a single users/customer. These roles and skillsets shall dictate what areas of the system the user or customer can access and what records and fields can be viewed and or edited. The role assigned to a user shall also dictate which templates/reports they will have the ability to see and run. It is intended that roles and skillsets shall allow workflows to automatically assign tasks to users with predefined skillsets/roles and to automatically shift tasks between users once the case has reached a predefined status necessitating a change in users’ skillset/role. By linking roles and skillsets to staff competency it is envisaged that the system shall allow areas of weakness within the staff competency matrix to be readily identified.
| 157 | The system shall support time recording. There shall be the ability to assign different salary costs for different officers or roles to allow the cost of an intervention to be calculated or an officer's productivity.
| 158 | The system shall be provided with an integrated tool capable of measuring different scaled plans.
| 159 | The system shall automatically insert data into dependant fields subject to rules, e.g. where user selects an address from the gazetteer, the parish and ward fields shall be automatically populated. There shall be a facility to override this where necessary.
| 160 | Users shall be capable of recording site inspections and outcomes for sufficient numbers of inspection types as required by users. The Council shall be able to create and customise inspection types, with sufficient numbers of user defined fields. Depending on the type of inspection type selected, the system shall pull through the necessary fields to be populated (as previously defined by the Council when setting up the inspection type).
| 161 | Inspections shall be able to calculate scheduled inspection dates based on pre-set and customisable inspection criteria and timescales, the rules for which shall be easily programmable by system admin users. Users shall be able to override the automated scheduling. Users shall be able to add additional diarised actions without overwriting the automated scheduling.
| 162 | The system shall be capable of creating and displaying any statutory public register online using any data contained within the system including spatially captured data.
| 163 | Key work tasks should have user definable dates for action and set reminders in the work diary and be fully reportable
| 164 | A comprehensive audit trail of all entries and status changes made within the system must be securely held and auditable for management purposes. The system must log user access events as well as data changes. The function shall display the date, time and user for any data changes performed. The audit function shall apply to all information coming into and out of the system including the opening of records/documents when they are read but not updated by the user.
| 165 | Provision of user-defined searching facilities within the system, which can retrieve specific applications, service requests and premises details by searching against registration number, address, trade as name, person etc. The system must be able to search by multiple fields.
| 166 | The applications shall link to the councils GIS and BS7666 addressing infrastructure and all addresses shall be derived from this infrastructure and shall update automatically when the corporate address is updated.
| 167 | Ability to use a unique dummy UPRN's when creating records for an address which does not exist on the system.
| 168 | The GIS Interface shall provide tools to: - - Geo-reference images - On the fly spatial analysis - Plot point, line and polygon features - Copy, edit polygon - Capture multiple location polygons for a single case record - Measure existing features automatically - Map printing - Zoom to & pan to selected features - Search for an address from the corporate address database - Measure new features via button clicks - Add new layers - Creation of buffer zones. - Capability to view additional MapInfo tab files by adding via layer control -The tool shall also allow for the measuring of areas and calculating angles.
| 169 | Spatially enabled integrated solution (generate case record from plotting boundary of the application on GIS to populate fields in the database from MapInfo tab files)
| 170 | The application shall draw data from the corporate GIS solution and/or other corporate applications to allow: - addresses be extracted from a GIS by either drawing boundaries or selecting individual properties - Selection of neighbours based on spatial data from corporate addressing data - Auto-generate consultees from spatial layer - Analysis of spatial data from the corporate GIS - Analysis and linking of property or person based records The system shall record details of all representations sent and received responses which shall be automatically assigned to the appropriate record in the system. The data received shall be editable and red actable (where allowed by the file type).
| 171 | The system shall provide a user configurable dashboard to display and enable the reporting of all information held within the system in multiple formats, e.g. graphs and tables.
| 172 | The system shall be capable of receiving and submitting data and documents via multiple sources (Including but not restricted to Web Portals, Gov.uk, Planning Portal, Submit-a-Plan, National Land Information Service (NLIS), Competent Persons Scheme, HMLR Land Charges System either in real time or by batch processing. The above shall allow applicants to resubmit application with modifications including updated plans.
| 173 | The system to allow users to have multiple case files open at any one time to allow updating and responding to enquiries.
| 174 | Ability for officers and managers to view, monitor and reassign workload tasks via a dashboard without the need to drill down within the system. The system shall be able to send automated notifications to a user when a task has been assigned to them.
| 175 | The system to have an escalation process to send alerts to users (officers and line managers) when an action has not been progressed within specified timescales. The rules governing this may be customisable and easy to create, update and delete. The system may enable work to be reallocated between users, on a case by case basis or as a batched process.
| 176 | The system to allow customisable embedded workflow processes for all service functions and processes.
| 177 | View a configurable dashboard of all cases on system start up including, for instance; -List of new cases -List of open cases with additional actions / updates -List of cases approaching KPI breaches -List of cases breached -Case status -Cases closed in last X days -List of cases by Case Officer
| 178 | When users are expecting to work in the absence of a live data connection, the system shall allow users to download any information already within the system to their mobile device .Officers can continue to use the system on a mobile device when they are out of signal / Wi-Fi range. Users shall be able to upload any work completed offline to the relevant case/record once a live data connection has been re-established.
| 179 | The system shall be capable of producing a series of mobile eForms, for easy capture of information by officers during visits. The data should be automatically saved against the relevant case record when mobile device has access to the main back office system. Wirral Council to have the ability to create new and amend existing eForms as part of the Support & Maintenance Agreement (ie no additional cost).
| 180 | Officers time can be captured within eform, for time spent on a visit; to record the date and time of when an inspection was started and finished.
| 181 | Users whilst field working should have the ability within the mobile working solution to produce documents, take photographs, add notes, attach them all to a report/form and email to Customer during site visit.
| 182 | The software shall have a Document Management System (DMS) that is either embedded within the application or it is fully/seamlessly integrated with an external document management system e.g Sharepoint. The opening of documents shall not necessitate departing from the case file to which it is attached. The system shall allow for documents of any format to be stored and viewed (provided locally required software is available).
| 183 | The system shall allow users to drag and drop multiple documents at once and attach them to a property/case/customer profile. The system shall allow system users to delete and amend attached documents dependent on their security privileges. All documents attached to records, cases or customer profiles shall be instantly available to all users with appropriate security privileges.
| 184 | It shall be possible to record and change the name and status of attached documents. e.g. Plans submitted can be designated super-ceded, approved or refused which would also be displayed online, once reviewed by an Officer. Ability to mark documents in DMS as public, private and consultee etc.
| 185 | There is a requirement for a direct link to Microsoft Outlook with the ability to upload incoming emails to a case record along with any attachments directly into the DMS system, via drag and drop function.
| 186 | The system has the capability to allow the import and storage of information in a variety of mediums including photographs, maps, letters, forms, emails, videos and sound recordings against an associated record.
| 187 | To have the capability to digitally stamp plans as approved/refused/superceded etc on the appropriate drawing plus a field within DMS for each document to be marked/updated to show status of each drawing submitted. This field could be displayed online so the public can quickly identify the status of plans.
| 188 | The system shall have the ability to redact any information from documents submitted/uploaded. This shall either be provided within the system itself or be compatible with third party software to redact documents.
| 189 | The system to have the ability to allow for the production of bespoke reports, with Wirral corporate styling, which can be displayed in a dashboard, in a variety of charts, with the capability of exporting the results of any query or report generated into Microsoft Excel, Word, Adobe Acrobat and other popular file formats or via 3rd party reporting tool such as Power Bi.
| 190 | Produce quarterly or annual Statutory Returns as required for Development Management, Building Control, Land Charges. e.g LABC KPI's/Annual BCPSAG
| 191 | Ability to generate and email reports to external Agencies i.e. Fire Service, Police.
| 192 | A suite of standard Management performance reports detailing current operational processes within user-defined timescales. The system must have the ability to modify these reports by format, fields etc. Minimum requirement to produce relevant management reports on the Key Performance Indicators specified by the Directorate/Office of the Chief Executive. Provide examples of management reports The system shall allow for the scheduling of reports and templates to auto generate.
| 193 | Customers can go to Wirral Council website and access and complete online forms via Wirral Council’s (Firmstep) customer account portal; using any device i.e. laptop, tablet or smartphone with a document upload facility 24/7/365; Customer can make applications, respond to consultations, book appointments, pay fees, report/request services online for any of the services detailed in this document; and have the ability to upload documents, photographs, videos and audio recordings, with automatic upload of submitted data into back office system.
| 194 | Customers can track progress of their submission. An automatic confirmation message with a reference number should be automatically sent to a customer, where appropriate, with a link where a customer can log into their account to track progress of their request.
| 195 | The system must seamlessly integrate with the Council's financial system to enable tracking and payment of invoices; payments made will need to be receipted in your system. This is to be a seamless process for the customer to be taken through the steps without noticing they are moving between different systems. Payments to automatically update the back-office system with receipt of payments details.
| 196 | Customers have the facility to search for their application/complaint/enquiry using wildcard/fuzzy searches type functionality.
| 197 | Facility to provide a Land Charges "Personal Search" browser based self-service module.
METHOD STATEMENTS
| 1 | Please describe how your solution will meet the requirements detailed in the tender document under Common ICT Requirements whilst complying with the attached Wirral Council ICT Security Policy |  | 20%
| 2 | Please describe how your organisation will meet the requirements within the tender document - Requirements. 1 to 197 |  | 65%
| 3 | We require the tenderer to provide three case studies to show a proven track record of successful projects in this field, most notably in the provision of a similar solution to the Council’s local authority peers or similar organisations, taking into account size, nature and complexity. |  | 2%
| 4 | Describe your implementation approach relating to this project. As a minimum, detail any proposals relating to: • System implementation • System migration • Timescale, processes • Support to update relevant operational working procedures • Staff training Explain any continuity of service implications for the service during this period. |  | 5%
| 5 | • Please provide details of your going Support for this system, • Please provide details of your escalation procedures should we experience any issues, problems with your solution. |  | 2%
| 6 | Please provide how you will manage and communication any system upgrades |  | 2%
| 7 | Please provide details of your weekly, monthly report and management functions. We would expect Management Information report and information, please provide details how you would meet these requirements. |  | 2%
| 8 | Describe how your solution will integrate with our current system as outlined within this tender documentation and the urgent supplier information appendix A. |  | 2%
PRICING SCHEDULE
price
|  | LOT 2 |  |  |  |  | Tenderers are required to complete the compliance table below. This table will form a critical part of the appraisal process. (These will replicate method statements for compliance purposes).
| 1 | The system shall be capable of recording various inspection types, including Food, PPC, H&S, Housing, Non-food, Animal Feed and were required calculate required ratings and next due dates as required by statutory legislation.
| 2 | Records and any attached documents to be able to be downloaded and used offline.
| 3 | The system shall be capable of receiving processing and generating all types of licence applications (different to those dealt with by the Licensing Team) including Licensing of Activities Involving Animals, Premises & Person Licenses for - Tattooing / Ear Piercing / Body Piercing / Semi-Permanent Make-up / Electrolysis etc, and Caravan Sites. Where applicable the system should be capable of calculating renewal dates in line with statutory guidance.
| 4 | The system shall be capable of receiving and submitting data and documents via multiple sources (Including but not restricted to Web Portals such as the Food Standards Agency business registration portal and Gov.uk)
| 5 | The ability as a statutory consultee to report any representations directly into the back office for both planning and licensing consultations whilst providing an audit trail/record of such representations.
| 6 | The system shall accept unique references from third party applications, when cases are created externally from the sources mentioned in item 4 above.
| 7 | The system shall have the ability to produce reports and extract data identifying work due between or before specified dates for inspections and licenses. The system shall have the ability for this work to automatically produce work records capable of being allocated to officers either individually or as a batch. Please explain how this is managed within the system.
| 8 | The system shall be capable of integration with a calendar / diary allowing the scheduling of appointments within the system.
| 9 | There should be the ability to accommodate appointments outside normal business/core hours to handle seasonal high demand for service and/or exceptional cases.
| 10 | Ability to search and interrogate past full history of complaints, persons, inspections, licenses requests for service as required by users in line with retention periods. Please set out any limitations when working on site e.g. without a data signal and also make reference to overall system data migration limitations.
Migration of any data from existing system must include all attachments to records including emails, photographs, word documents, PDFs, etc. Within retention period
| 11 | As well as basic mandatory fields, the user shall have the ability to reject requests for service where the application criteria has not been met or the information is deemed insufficient by the user. For example when applying for a license or requesting a food hygiene revisit where the quality of information requires user approval/rejection.
| 12 | The system should be capable of automatically generating standard response / informative emails or letters on receipt of certain identified types of service requests.
| 13 | The system shall have the ability to link complaints from multiple sources against the same premises.
| 14 | The system shall have a record locking or alert mechanism to prevent multiple users editing the same record concurrently. The system shall alert the user the record is currently in use and identify the user.
| 15 | The system has the ability to monitor and report on scheduled actions that are due/overdue e.g. return noise log sheet, respond to letter, notice period expired etc.
| 16 | On closing premises records, inspection ‘next due’ dates should be removed, and the premises records not included in any subsequent uploads of data to external agencies websites or workload reports.
| 17 | The system must provide a facility to place ‘alerts’ against properties, people, or vehicles, to alert other users to a particular matter. Please explain how this is achieved.
| 18 | Please explain how the system can create multiple business records against the same property index reference. For example where a food business (more than one) may be based at a single domestic address.
| 19 | The system shall have the ability for providing fields to allow bespoke codes to be entered against records to enable the information to be extracted as required both by statutory reports / legislative requirements for example LAEMS or FHRS and also in-house campaigns etc
| 20 | The system shall be capable of producing mail merge documents for premises selected from the database records or where this is not possible the ability to export premises details to Microsoft Excel or equivalent for the same purpose.
| 21 | The system shall be capable of producing reports whilst on site at businesses or dwellings that can be sent via email or letter when a signal is available
| 22 | The system shall include a mobile solution to enable the functionality as specified in the generic IT requirements to be met for Environmental Health across a range of general activities and interventions (See 23 below too).
| 23 | Expanding on point 22 above, specific functionality shall be available to officers when onsite conducting a food hygiene inspection. And in particular include: • recording of information during an inspection • review of historical compliance data whilst on site • generate a report to be emailed (subject to data signal) whilst on site to the owner • other tools to support the above are integrated for example standard paragraphs, templates, translation, GPS, dictation, photo annotation,
| 24 | The system shall support time recording. There shall be the ability to assign different salary costs for different officers or roles to allow the cost of an intervention to be calculated or quantify a user’s productivity.
| 25 | The system shall have the ability to redact any information from documents submitted/uploaded. This shall either be provided within the system itself or be compatible with third party software to redact documents.
| 26 | Environmental Health as a high risk statutory service must go-live with full functionality required to deliver the service from start to finish on the same day (cannot be a phased approach) e.g. database, GIS functionality, online register and Document Management functionality all live on the same day. Please explain your approach to this and set out any limitations.
| 27 | The system to allow the input of an out of area address for contacts
| 28 | When users are expecting to work in the absence of a live data connection, the system shall allow users to download any information already within the system to their mobile device including but not limited to: • Existing documents • Workflows • Case records • Property history • Customer profiles The system shall enable documents to be downloaded individually and in batches of any size. The system shall have to ability to make information available offline however the Council are not prescribing the method by which this can be achieved. Suppliers shall provide evidence as to how their product fulfils this requirement.
| 29 | Users shall be able to upload any work completed offline to the relevant case/record once a live data connection has been re-established. Please also explain any limitations to this.
| 30 | Users undertaking an inspection whilst onsite can take photographs via the mobile device, attach them to an inspection report, including any data and add notes to the photograph
| 31 | For the purposes of allocation and case management, managers and officers must have the ability to view a configurable dashboard of all cases which should include: • List of new cases contained in a holding area or similar awaiting allocation to an officer • Sort/filter/view lists/workloads by case-type (e.g. complaint, inspection, application) • List of open cases with additional actions / updates • List of cases approaching service standards breach/time-out • List of cases breached service standards • Case status • Cases received/closed in last X days • List of cases by Officer
| 32 | In addition to 31 above, managers shall be able to extract data and generate reports from the service and individual officers for the purposes of performance management
| 33 | The system should have the facility to record investigations/prosecutions which must incorporate all relevant details including associated dates, outcomes, and costs awarded by Courts
Pest Control Specific Requirements (as part of Environmental Health)
| 34 | The system must be capable of recording/capturing detailed information regarding a pest problem at source via any access channel i.e. online, telephone, personal visit to a council office including any special information such as access restrictions or instructions
| 35 | The system should have the ability to raise a pest complaint where an address has not yet been added to the Local Land & Property Gazetteer
| 36 | The system shall be capable of integration with a calendar / diary allowing the scheduling of appointments within the system. The system should have the ability to schedule jobs for: • Operator/Inspector resource availability / working pattern • Complaint location (postcode based) • Groups of wards into districts – North Wirral, South Wirral, East Wirral, West Wirral Type of complaint (residential / commercial)
| 37 | The appointment/calendar functionality will be configurable to accommodate/differentiate domestic and commercial premises requests/jobs. The back-office system and booking system shall be configurable to limit by ward/districts and to have the availability of appointments to be booked to allow for efficient route planning.
| 38 | The system is to have the ability to block book calendars/hide calendars; Manual override control of the calendar by managers. For example where staff and thus appointments are not available due to holidays, training etc.
| 39 | There should be the ability to accommodate appointments outside normal business core hours to handle seasonal high demand for service.
| 40 | The system should have the ability to search and interrogate past full history of complaints, treatments, visits
| 41 | The back-office system and mobile working application may integrate with a mapping system to provide route planning to officer’s appointments.
| 42 | The booking process has the ability for customers and staff to request the service, book an appointment, book a number of revisits, make a payment for the service at the point of request, payments must interface with Wirral’s corporate payment applications as described earlier in this tender.
| 43 | For chargeable work where an invoice would need to be generated i.e. commercial premises contracts, school contracts, the system should interface with Wirral’s Enterprise Resource Planning solution
| 44 | The system to have the ability to recognise the difference between new pest control service requests and pest control revisits, be those revisits scheduled or requested, by type of service.
| 45 | Customers and staff must have the ability to update the pending service request and change the allocated appointment (or add information), and that this will automatically change or prompt a change to the revisit date to ensure it remains within the correct revisit timeframe specification.
| 46 | For customers and staff to have the ability to cancel a request, generating a refund request, if the cancellation is before the first visit
| 47 | Managers and officers have the ability to assess and manage current workloads via a dashboard
| 48 | For the system to have the ability to record information where a customer wants to delegate responsibility when requesting the service digitally, to a third party to allow a pest Control Officer access to premises for a first visit by that person, or alternatively holding written authority (which would later be “scanned in”) from the owner / occupier, and also being able to satisfy risk assessment enquiries from the Pest Control Officer.
| 49 | Pest Control Officers can send external emails out of the system to customers with attached additional information pages (e.g. bird feeding advice or poultry advice
| 50 | For customers to be able to request verbal advice on a pest problem, the system to allow customers to book a “telephone meeting” with the service, pay for the service at the point of contact. For the request to route to a Pest Control manager/workload, and once completed for the request to be closed.
TRADING STANDARDS
| 1 | Explain how the solution will enable the recording of various inspection types, including food standards, weights and measures. product safety, feed standards including calculating ratings and next inspection due date as required by statutory legislation.
| 2 | Explain how the solution will interact with the Citizen Advice Bureau Partner Portal to download notifications and referrals.
| 3 | Explain how the solution can be utilised for agile/mobile working away from the office, without a live data connection, including the ability to carry out the following: • Records and any attached documents may be able to be downloaded and accessed offline • Reports can be produced onsite and then be sent by email or letter • Access to case records, workflows, property history, customer profiles • Take photographs via a mobile device and attach them to an inspection report, including adding any data or notes to the photograph • Apply an electronic signature to documents
| 4 | Explain how the solution will enable users to upload any work completed offline to the relevant case/record once a live data connection has been re-established
| 5 | Demonstrate that when using this solution an officer can view a configurable dashboard of all cases which includes: • List of new cases • List of case type • List of open cases with additional actions/updates • List of cases approaching service standards breach • Case status • Case closed in last “X” days • List of cases by officer
| 6 | Demonstrate that the solution has the capability to: • Record the time of processes • A facility to record investigations and prosecutions including relevant details • Integrate with a calendar or diary allowing the scheduling of appointments within the system • Link complaints from multiple sources against the same premise • Producing all types of licences • Create multiple business records against the same property index reference • Redact any information from documents submitted or uploaded • Allows for the input of out of area address or contacts • Allows for the search and to interrogate past full history of complaints, persons, inspections, licence requests for service as required by users.
| 7 | Demonstrate the solution has the capability to: • Create a legal action file • Record actions taken by officer • Support time recording with an ability to assign different salary costs for different roles/officers • Record dates of outcomes • Record costs awarded by Court
| 8 | Demonstrate that the solution can produce reports and extract data identifying work due between or before specified dates for inspections and to produce work records capable of being allocated to officer’s either individually or as a batch
| 9 | Demonstrate that the solution has an alert or locking mechanism to prevent multiple users editing the same record concurrently and alerts the user that the record is currently in use and identifies the user.
| 10 | Demonstrate that the solution has the ability for providing fields to allow codes to be entered against records to enable information to be extracted as required by statutory reports/legislative requirements such as LAEMS or FHRS
| 11 | Demonstrate that the system allows for when premises are closed, inspection “next due” dates are removed and the premise records are not included in any subsequent uploads of data to external agencies websites
| 12 | Demonstrate that the system has the facility to place an “alert” against properties, people or vehicles to alert other users to a particular issue or matter.
| 13 | Demonstrate that the system is capable of receiving and submitting data and documents via multiple sources including but not restricted to web portals or Gov.UK
HOUSING SERVICES
| 1 | The solution should enable the recording of financial information related to grants and/or loans including, calculating payments, the ability to split payments into component parts e.g. fees, contractor payments, land registry payment etc., providing robust audit trails and have the ability to lock down historical information at key stages to prevent future alterations. The solution should ideally have the ability to integrate with the Council’s existing payment software and corporate Oracle software. If it cannot, it should be an option for development.
| 2 | The solution should enable the recording of financial information related to HMO & Selective Licensing, including staged payments. The solution should ideally have the ability to seamlessly integrate with the Council’s existing payments software & Oracle software. If it cannot, it should be an option for development.
| 3 | The solution should have the ability to facilitate Mobile/agile working away from the office, including the ability to: • Undertake and record surveys of buildings including HHSRS • Customer satisfaction surveys • Equal opportunity data collection • Complete a range of electronic applications for financial support (including secure electronic signatures), • Use electronic pen/or other suitable alternative method to record free text on the system • To record photographs and videos taken on site and to seamlessly attach to case files • Generate and send emails and certain defined standard documents/reports, whether manually or automatically • Access and make amendments to officer Outlook diaries • Plan the most efficient travel routes between appointments (possibly using GPS) and any other agile functions your solution has that would assist in a move towards both a paperless office and more efficient working.
| 4 | The solution should be able to generate reports from the data held, including data across different services. It should have the capability to create specific bespoke reports related to the Housing Standards functions, including, for example: Identify approved, committed & spent grant/loan expenditure including fees and contractor details Numbers and types of specific legal notices served, notices expired without compliance, notices complied with Number of selective licences issued in specific geographical areas
| 5 | The solution should enable the creation of schedules of works using both standard and bespoke user defined paragraphs. To include the ability to use a user defined schedule of rates for specified works and display information in various formats
| 6 | The solution should record information related to statutory appeals and default works, including the full range of enforcement action, Civil Penalties and Rent Repayment Orders and both Selective and Mandatory HMO licensing. The solution should include such items as, key dates, actions taken, outcome(s) and financial information, including contractor payments. This list is not exhaustive.
| 7 | Staff should be able to search for a property or case and see all customer profiles and associated case records linked to that property/case and to drill down into its complete history for all disciplines within the system for which they have security privileges
| 8 | The solution must be capable of producing all types of mandatory House in Multiple Occupation and Selective Licences and Landlord Accreditations using data held in the system
| 9 | The solution should automatically generate an email and/or letter to Licence holders based upon a pre-renewal date set by users (e.g. 30 days before licence is due to expire). In addition, the solution should automatically notify licence holders by email or letter where a license has for a House in Multiple Occupation, a Selective Licenses or a Landlord Accreditation has expired based upon an expiry date
| 10 | The solution should notify officers when scheduled actions are due e.g. where no response has been received following issuing of a letter, or where service standards are close to, or have been, breached
| 11 | The solution should check customer details at point of entry to ensure duplicates are not entered on the database
| 12 | The solution should enable the user to configure a dashboard showing certain summary information, including such things as: • List of new cases • List by case-type (e.g. complaint, inspection, application etc) • List of open cases • List of cases approaching service standards breach • List of cases where there has been a service standards breach • List of open cases by officers • List of grant/loan applications awaiting approval or payment • Cases which have been designated as a Priority 1 And be able of sending automated notifications to a user when a process has been assigned to them. In addition, the solution should be capable of displaying user defined information including key stages such as target dates, milestones on one screen to enable managers to access and monitor record information without having to drill into the property records
| 13 | Service users should be able to apply directly for HMO and Selective Licenses, landlord accreditation and Financial Assistance (Grant & Loan) an explanation of how this is done using the solution from start to finish should be included in the method statement. This should include the various stages of the application process, including providing evidence via uploading of documents/photographs and emails, on-line payments, client financial information and any automated document production. The solution should allow for the ongoing maintenance of a license once issued. This should include the issuing of licence revocations, variations and temporary exemption notices and providing public registers. Information entered by the service user should automatically populate the back-office records and the solution should have the ability for the applicant/service user to save and leave a partly completed application and return at a later stage to complete the application, including a function to warn any user prior to the timeout of a session so it can be saved or recommended
| 14 | The solution should have the capability of being maintained in line with any new legislation/statutory powers introduced related to Private Sector Housing activity
| 15 | The solution should enable inspecting officers to fully use the Health and Safety Rating System, which should include as least the recording the inspection findings, scoring and use of photographs. The various components of HHSRS including hazard type, score, overall rating etc should be capable of being reported on
| 16 | The solution should produce documentation and store records relating to the full range of statutory actions available for private sector housing, including enforcement action, civil penalties, rent repayment orders, fit and proper person records, banning orders, CPOs, enforced sale and Interim/Management Orders. This should include the ability to monitor progress with the actions.
| 17 | The solution should record actions related to empty residential properties and bringing empty residential properties back into use. This should include the ability to monitor progress with the actions
| 18 | The solution should interface/integrate with Ferret Renovator Means Test Calculator (or other appropriate solution) and must therefore support relevant software with the ability to undertake the Government prescribed means test calculation as defined by legislation; to ensure a seamless DFG grant application process without delay.
| 19 | The solution should ideally have the ability to enable service users to book appointments, integrating directly with case officer electronic diaries (Microsoft Outlook). If is cannot do this is should be capable of being developed
| 20 | In relation to Financial Assistance Products (Grants/Loans) the solution should identify and report on at task level, approved, committed & spent grant expenditure including fees client contribution and identify/record/calculate separate multiple capital funding sources for pooled funding cases over £30k or cost sharing., As well as recording / reporting adaptation classification and type (i.e. stair lift, level access shower), client classification
| 21 | The solution should have the ability to add bespoke fields with the functionality to create and add, remove and amend communal system coding functions as and when required. Eg application types
| 22 | The solution will allow users to have multiple case files open at any one time to allow updating and responding to enquiries.
| 23 | The solution should interface with other preferred related solutions “bolt on’s” (API’s) required by the services now and in the future; in relation to Adaptations please explain in the method statement how the solution would interface with the electronic drawing package “Idapt” currently used by the Service.
| 24 | In relation to Financial Assistance Products (Grants/Loans) the solution should support effective and efficient case management to avoid delay, ensuring key steps in the process are undertaken in the correct order and case transfer between officer/process, tasks are identified, executed and easily managed & monitored.
LICENSING
| 1 | The system shall be capable of receiving and submitting data and documents via multiple sources (Including but not restricted to Web Portals and Gov.uk) either in real time or by batch processing. The above shall allow applicants to resubmit application with modifications including updated plans, please advise how you will enable this.
| 2 | The system shall be capable of receiving and dealing with all type of licence applications for licensed premises, personal licenses - taxis and private hire (vehicles, drivers, and operators), scrap metal dealers, gambling premises, house-to-house collections, street trading, pavement cafés, sexual entertainment venues, marriage premises, temporary event notices, complaints, etc. the system should be capable of being adapted to encompass any future licence types which may become part of core business due to legislative or local changes
| 3 | The system shall accept unique references from third party applications, when cases are created externally from the sources mentioned above
| 4 | Ability to view a configurable dashboard of all cases which should include: • List of new cases • List by case-type (e.g. complaint, inspection, application) • List of open cases with additional actions/updates • List of cases approaching Service Standards breach (e.g. contact not been made, or visit not taken place within ‘X’ days) • List of cases that breached Service Standards • Case status • Cases closed in last ‘X’ days • List of cases by Officer
| 5 | The system to have address validation via UPRN with online mapping and integration to council LLPG to prevent duplicate address entries
| 6 | Users should be able to look up a property and see all customer profiles and associated case records linked to that property and drill down into its complete history for all disciplines within the system for which they have security privileges
| 7 | The system should provide a global search facility for search terms including a person’s name, date of birth, vehicle registration number, licence number, vehicle make/model, vehicle colour. The search engine should make suggestions based upon the search term entered i.e. system should suggest ‘the king’s head’ in its results if only ‘kings head’ was entered by a user
| 8 | The system should allow a user to search for a designated premise supervisor (DPS) by name, with the system returning all results where that person is the DPS
| 9 | The system should be able to record different types of licensed premises against properties, including off-licence, pub, club, bar, restaurant, hotel, etc. The system should be able to return search results for these different types of premises
| 10 | The system should be capable of producing all types of licences using data held in the system
| 11 | The system should be able to produce a licence card incorporating data held on the system, including a licence holders photograph. This licence card should be able to be sent to a badge printer for printing
| 12 | The system should be capable of automatically generating emails or letters to licence holders based upon a pre-renewal date set by users (e.g. 30 days before licence is due to expire). This allows documentation to be sent to licence holders advising their licence is due for renewal
| 13 | Automatically notify users where licences have expired based upon an expiry date
| 14 | Manage and automate correspondence with Responsible Authorities in relation to Licensing act 2003 applications
| 15 | Allow Responsible Authorities to make representations / comments directly into the back office in relation to Licensing act 2003 applications
| 16 | Receive alerts from within the system where scheduled actions are due e.g. where no response has been received following issuing of a letter, or where service standards are close to, or have been, breached
| 17 | The system must have built-in processes to ensure that customers details are checked against the system at point of entry to ensure duplicates are not entered on the system
| 18 | The system must provide a facility to place ‘alerts’ against properties, people, or vehicles, to alert other users to a particular matter
| 19 | The system should automatically close a taxi or private hire driver application if it the licence is not issued within a set period from the receipt of the application e.g. 6 months. The system should automatically generate an email to the applicant advising them of the closure of the application
| 20 | The system should be capable of recording all instances where an applicant or licence holder is referred to a Committee, and should store the associated report and outcome decision
| 21 | The system should have the facility to record investigations/prosecutions of licence holders which must incorporate all relevant details including associated dates, outcomes, and costs awarded by Courts
| 22 | The system should have the facility to record appeals lodged by applicants or licence holders which must incorporate all relevant details including associated dates, and outcomes
| 23 | The system should provide the facility to interrogate data held against licence holders and produce reports on specific fields
| 24 | The system should be capable of time-recording of processes
| 25 | Migration of any data from existing system must include all attachments to records including emails, photographs, word documents, PDFs, etc
| 26 | The system should provide the facility to search and interrogate past full history of complaints, persons, inspections, licenses requests for service as required by users
| 27 | The system must be capable of interfacing with DEFRA in relation to maintaining a centralised database of taxi and private hire vehicles in order that the Council’s requirements under The Air Quality (Taxi and Private Hire Vehicles Database) (England and Wales) Regulations 2019 are met. Such interfacing must be compatible with RESTful API
Method Statements
| 1 | Please describe how your solution will meet all relevant Common ICT Requirements whilst complying with the attached Wirral Council ICT Security Policy |  | 10%
| 2 | Please describe how your organisation will meet the Generic Core Business requirements within this tender documentation |  | 10%
| 3 | Please describe how your organisation will meet the service/public access specifications requested for all Regulatory services within this documentation? |  | 5%
| 4 | Please describe how your organisation will meet the Environmental Health (inc Pest Control) requirements within this documentation including, where relevant, if further development is needed to meet the specification, how long this will take and whether or not such development will incur additional expenditure for the Council in addition to the costs associated with the initial provision of the solution. Please also provide examples of other local authorities where you have provided a similar solution to those specified in section 2. Please be specific e.g. name the authority and specific solution Your answer should refer to the all requirements contained in the specification. |  | 13%
| 5 | Please describe how your organisation will meet the Trading Standards requirements within this documentation including, where relevant, if further development is needed to meet the specification, how long this will take and whether or not such development will incur additional expenditure for the Council in addition to the costs associated with the initial provision of the solution. Please also provide examples of other local authorities where you have provided a similar solution to those specified within this documentation. Please be specific e.g. name the authority and specific solution Your answer should refer to the all requirements contained in the specification. |  | 13%
| 6 | Please describe how your organisation will meet the Licensing requirements within this documentation including, where relevant, if further development is needed to meet the specification, how long this will take and whether or not such development will incur additional expenditure for the Council in addition to the costs associated with the initial provision of the solution. The system shall initially be capable of receiving and dealing with all type of licences as outlined within this documentation. How adaptable is your system in relation to encompassing any future licence types which may become part of core business due to legislative or local changes? Explain the process for creating new licence types within your system. Please also provide examples of other local authorities where you have provided a similar solution to those specified within this documentation. Please be specific e.g. name the authority and specific solution. Your answer should refer to the all requirements contained in the specification. |  | 13%
| 7 | Please describe how your organisation will meet the Housing Standards requirements within this documentation including, where relevant, if further development is needed to meet the specification, how long this will take and whether or not such development will incur additional expenditure for the Council in addition to the costs associated with the initial provision of the solution. Please also provide examples of other local authorities where you have provided a similar solution to those specified in section 2. Please be specific e.g. name the authority and specific solution Please Note - your description of how you meet the Housing Standards requirements must encompass a response to each of the individual numbered items listed within this documentation |  | 13%
| 8 | Performance management: For each area of work it must be possible to highlight performance that is good or approaching good, poor or approaching poor with the parameters for each performance threshold being set locally. These performance thresholds should be easy to change so that Wirral staff can do so. The supplier should detail how this facility is to be delivered. Please also provide details of your weekly/monthly report and management functions. We would expect Management Information Report and information to be extracted by managers to assess both officer and service performance, please provide details how you would meet these requirements. |  | 5%
| 9 | Describe your implementation approach relating to this project. As a minimum, detail any proposals relating to: • System implementation • System migration • Timescale, processes • Support to update relevant operational working procedures • Staff training Explain any continuity of service implications for the service during this period. Describe how your solution will integrate with our current system as outlined within this documentation. |  | 10% |  |  | Please note that for each method statement question, the final score is the result of a moderation process which produces an average score. If a bidder scores a 2 or less for any Method Statements on more than 2 occasions, they will be removed from the tender process.
| 10 | Please provide details of your going Support for this system, Please provide details of your escalation procedures should we experience any issues, problems with your solution. |  | 4%
| 11 | Please provide how you will manage and communicate any system upgrades |  | 4%
PRICING SCHEDULE
Price
Not applicable
Not ready
Ready for review
Extensive re-work
Minor comments
Approved / Complete

## Clarifications
Wirral Metropolitan Borough Council - Regulatory & Enviromental Services Replacement Software - CRM 103501 | [7 empty] | Wirral Metropolitan Borough Council - Regulatory & Enviromental Services Replacement Software - CRM 103501
NPS Reference | Client Reference | Clarification raised | Date submitted | Competitor or NPS clarification | Requested by | Clarification response | Date received

## Resources and Availability
Wirral Metropolitan Borough Council - Regulatory & Enviromental Services Replacement Software - CRM 103501
[15 empty] | Resources & Availability | [30 empty] | Resources & Availability
[5 empty] | MONTH (copy these columns as many times as required) | [30 empty] | MONTH (copy these columns as many times as required)
| Name | Initials | Role | Notes | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
[7 empty] | Bid Kick-Off | [15 empty] | Blue Team |  |  |  | Red Team |  |  |  |  | Submission deadline
Sales Lead
Bid Director
Bid Manager
Solution Lead
Commercial Lead
Technical Architect
Finance
Legal
Transition Lead
Delivery Lead
Executive Sponsor
Delivery Sponsor
Sales Sponsor
Additional support as required to be provided by
Available
Limited availability (i.e. some diary commitments)
Unavailable (e.g. most / all day in meetings / annual leave)
Weekends and Bank holidays

## Actions
Wirral Metropolitan Borough Council - Regulatory & Enviromental Services Replacement Software - CRM 103501
Ref | Request / Action | Stage Requested | Date Requested | Deadline | Owner | Status | Notes
awaiting decision- bid or not to bid.

## Review Allocation Matrix
Wirral Metropolitan Borough Council - Regulatory & Enviromental Services Replacement Software - CRM 103501
Review Framework - Review Allocation Matrix and Scoring Sheet
Red Team - Allocation and Scoring Matrix
| Question | Original author | Review 1 | Review 2 | Review 3 | Minimum score | Min reached | Reviewer Score (0-4) | Review Status | General Comments
| Question 1 | xxx |  |  |  |  | 0 | 0
| Question 2 | xxx |  |  |  |  | 0 | 0
| Question 3 | xxx |  |  |  |  | 0 | 0
| Question 4 | xxx |  |  |  |  | 0 | 0
| Question 5 | xxx |  |  |  |  | 0 | 0
| Question 6 | xxx |  |  |  |  | 0 | 0
| Question 7 | xxx |  |  |  |  | 0 | 0
| Question 8 | xxx |  |  |  |  | 0 | 0
| Question 9 | xxx |  |  |  |  | 0 | 0
| Question 10 | xxx |  |  |  |  | 0 | 0
| Question 11 | xxx |  |  |  |  | 0 | 0
| Question 12 | xxx |  |  |  |  | 0 | 0
| Question 13 | xxx |  |  |  |  | 0 | 0
|  | xxx |  |  |  |  | 0 | 0
| Social Value | xxx |  |  |  |  | 0 | 0
[7 empty] | 0 | 0
[7 empty] | 0 | 0
[7 empty] | 0 | 0
[7 empty] | 0 | 0
Reviewers:
Cathryn Ella
Carol Webb
Lesley Davids
Ian Morissey
Note on B2: Lee Bradburn: This is an example - you should make appripriate for your bid.

## Evaluation Criteria
Wirral Metropolitan Borough Council - Regulatory & Enviromental Services Replacement Software - CRM 103501